## Sheet1
Feature ID | Feature/Action | Required behaviour | Current behaviour(s) | Pass/Fail | Status | Priority | Comments
QL001 | App/page is refreshed | To play audio from current playback position when pressed. An app refresh should not impact the current playback position. Whatever the usual rules about synching between devices should apply. | Play audio from current playback position when pressed. | Pass | Closed | low
QL002 | A Roll Back position is saved then the Play button is pressed | The Roll Back position is saved and the list updated. Ther should be no interference with the Playback at all. | The audio position is reset back to the start of the current Juz position (i.e. 00:00 of the Juz selected currently in the drop down above the Playback Progress Bar) | Fail | Active
QL003 | Pressing the Play button after App/page refresh | To play audio from current playback position when pressed. An app refresh should not impact the current playback position. Whatever the usual rules about synching between devices should apply. | 1. After page/app refresh, clicking the play button plays the audio from the start of the current Juz, which acts like the Reset button. This should not happen. 2. Playback Progress Bar head does not progress nor does its audio playback's Elapse or Remaining time (with or without speed adjustments). The precentage progress pill beneath the Playback Progress Bar does not update. The only way to make these update is to press keep play and pause several times. 3. The Mushaf Quranic text/translation does not progress from page to page like under normal circumstances | Fail | Active
QL004 | To play audio from current playback position when pressed. An app refresh should not impact the current playback position. Whatever the usual rules about synching between devices should apply. | The Playback Progress Bar head moves to the selected Roll Back position and audio begin to play from that position. | Playback Progress Bar head moves to the correct position, but the audio plays from wherever it reached after the App/page was refreshed, and not from the correctly selected Roll Back position. | Fail | Active
QL005 | After App/page refresh, the Ayat drop down is selected and an Ayat/verse is chosen. | The Playback Progress Bar head moves to the selected Ayat/verse position and audio begin to play from that position. | Playback Progress Bar head moves to the correct position, but the audio plays from wherever it reached after the App/page was refreshed, and not from the correctly selected Roll Back position. | Fail | Active
QL006 | After App/page refresh, the Backward and Forward buttons in the Playback area are pressed one at a time while the audio is playing. | The Playback Progress Bar head moves to the selected position and audio begins to play from that position. | Playback Progress Bar head moves to the correct position, but the audio plays from wherever it reached after the App/page was refreshed, and not from the Backward/Forward button positions. | Fail | Active
QL007 | After App/page refresh, reset button is pressed in the Playback area | The Playback Progress Bar head moves to the start of the audiofile of the currently selected Juz (the currently set Juz on the Juz drop down -- which is above/north of the Playback Progress Bar) | Playback Progress Bar head moves to the correct position, but the audio plays from wherever it reached after the App/page was refreshed, and not from the Reset button position (which is the begin of the audiofile for that Juz). | Fail | Active
QL008 | Mushaf page turn speed | Mushaf pages should turn exactly on the Ayat/Verse starts to be read. | A Mushaf page is displayed a few miliseconds after the Ayat/verse has began being read. | Fail | Active |  | Consider preloading the next Ayat/vers in the Mushaf display to allow for a smoother transition
QL009 | Mushaf Quran.com/link | This needs to be moved to the bottom of the Mushaf pop up, underneath the English translation | The link for the Quran.com for the current verse is positioned in the header of the Mushaf popup. | Fail | Active
QL010 | Mushaf English Translation text | Remove the words "English Translation" | English Translation wording is there and causing clutter | Fail | Active
QL011 | Mushaf Translator | The name of the English translator should be in a box above the Quran.com link and below the actual translated text. It should allow you to navigate between exisiting translation using left and right arrows | Mushaf Translator name is in the wrong location, and missing a quick way to change between translators | Fail | Active
QL012 | Mushaf recitation & English translation | Remove the words "Mushaf recitation & English translation" | Mushaf recitation & English translation text is causing clutter | Fail | Active
QL013 | Mushaf current idea location in Juz | Remove the Mushaf current idea location in Juz. It looks like this: (Ayat 8 of 246 in this Juz) | Mushaf current idea location in Juz is causing clutter | Fail | Active
QL014 | Mushaf icon | Remve the icon of the book on the top left of the Mushaf popup | Mushaf icon is causing clutter | Fail | Active
QL015 | Mushaf Quranic text area | Remove the horizontal rule and the Script and Font info | Mushaf Quranic text area Script and Font info is causing clutter | Fail | Active
QL016 | Roll Back and Reading logs in Profile | Move these into the appropriate places in the App Settings | Both of these are now in the user Profile page and don't belong there | Fail | Active
QL017 | Pressing Match Audio | The audio time remaining and the Big Timer countdown should be in perfect synch (not a few miliseconds off from when the user pressed it). They should remain synched until the timer runs down to zero, at which point it counts up again or the audio track ends and Big Timer resets in someway. | When match is pressed they are initially in synch but over time they gradually become out of synch. This should not happen. | Fail | Active